## Bug Report
Bug ID | Severity | Component | Summary | Test | Scene | To reproduce | Expected outcome | Actual outcome | Screenshot | Fixed?
1 | 3 Minor Bug | Camera | Camera shakes | 1.2 | Level 1 | Run the game in fullscreen mode. Observe the location of the player. | The camera should be stabilised and follow the player who is positioned in the centre of the screen. screen . | The camera following the player shakes. | bug 1.png | yes
2 | 3 Minor Bug | Player Movement | The player is stuck with the surface. | 2.1.2 | Level 1 | Observe the player with the appropriate collider. | The player should have proper collider. | The player's head is stuck with other surfaces. | bug 2.png | yes
3 | 3Minor Bug | Jump | The player jumps inside a teleporter. | 2.2.1 | Level 1 | Press the space key, and the player jumps on the ground but not inside a teleporter. | The player should jump by pressing the space key when he is on the ground or not inside a teleporter. | The player should jump by pressing the space key when he is on the ground but not inside a teleporter. | bug 3.png | yes
4 | 3 Minor Bug | Moving Platform H | Horizontal Moving Platform obstructs with other static platform. | 3.1.1 | Level 1 | Test horizontal Moving Platforms that move along their x-axis and/or z-axis without obstruction. | Horizontal Moving Platforms should move along their x-axis and/or z-axis without obstruction. | Horizontal Moving Platform moves along their x-axis and/or z-axis obstructs with another static platform due to the distance setting. | bug 4.png | yes
5 | 3 Minor Bug | Chckpoint | The player is not respawning. | 4.4 | Level 1 | Respawn to the player at the checkpoint when the player is destroyed. | The player should respawn at the last checkpoint when the player is destroyed. | The player is not respawning at the last checkpoint but falling in the air constantly. | bug 5.png | yes
6 | 3 Minor Bug | Laser | The laser bean is out of range. | 5.1 | Level 1 | The laser beam is out of range. | The laser beans should have a designer-specified length. | The laser beans cast out the designer-specified length. | bug 6.png | yes
7 | 3 Minor Bug | Teleporter and Scene | The player is not teleporting to the beginning of the next scene. | 7.5 | Level 1 | Teleport to the beginning of a different level when pressing the space key while the player is inside the teleporter. | The player should teleport to the beginning of a different level when pressing the space key while he is inside the teleporter. | The player is not teleporting to the beginning of a different level when pressing the space key inside the teleporter. | bug 7.png | yes